## Slide 1
Project Closure Manual

## Slide 2
Project
Submission
Evaluation/Approval
Implementation
Closure

## Slide 3
At the end of the project implementation, several obligations arising from the Programme, the EU and the national legislation still apply.
The project clοsure procedures are being implemented by the Lead Beneficiary on the MIS.
Closure

## Slide 4
Through MIS
Final Progress Report
Examination by JS
Completion Decision
Final Application Form
Final Project Report (attached to the AF )
Mail Closure Procedures:

## Slide 5
The Lead Beneficiary, in collaboration with the partnership, must submit the FINAL PROJECT REPORT, no later than (2) months from the date of final verification.
It must be fill in, in English using the template and it has to be submitted to the JS electronically, via uploading on the MIS (https://logon.ops.gr/) attached to the AF for Project Completion
The Final Project Report contains a summary of the project implementation
It should provide an overview of the project’s activities and achievements. It should also highlight how cross-border cooperation has contributed to attain the expected results and should include a detailed description of the measures foreseen in order to ensure their durability.
It should contain financial information of all verified and/or certified expenditures,
It should provide an overview of communication and Publicity activities that have been implemented,
FINAL PROJECT REPORT

## Slide 6
It should
Provide an overview of the project’s activities and achievements.
Define the impact on Target groups and the added value of the project
Declare the indicators achievement
highlight how cross-border cooperation has contributed to attain the expected results
Include a detailed description of the measures foreseen in order to ensure their durability.
Provide an overview of Communication and Publicity activities that have been implemented
Contain financial information of all verified and/or certified expenditures,
FINAL PROJECT REPORT

## Slide 7
FINAL PROJECT REPORT

## Slide 8
FINAL PROJECT REPORT

## Slide 9
FINAL PROJECT REPORT

## Slide 10
Table 1: Financial overview of the project
FINAL PROJECT REPORT

## Slide 11
At the Final Project Report, the Lead Beneficiary must describe how the deliverables will be used after the end of the project:
When maintenance and operation is needed (infrastructures):
The Lead Beneficiary must indicate the existence of relevant entities/operational structures or to predict the needed actions, within a specific timeline, to ensure its maintenance and operation
When no operation is foreseen:
The Lead Beneficiary must describe the way the results will be used
FINAL PROJECT REPORT
Important Information

## Slide 12
Along with the main documents described above, the LB submits at minimum a comprehensive list of all deliverables per beneficiary, which has to be acknowledged by the JS. Core deliverables have to be available at any time, therefore they must be stored electronically (drive folder with open access and/or otherwise i.e. on the project website) and attached (copy the drive link) in the relevant field of the AF (Beneficiary comments)

## Slide 13
ATTACHED LIST OF DELIVERABLES

## Slide 14
Steps during the project closure period
Activity/ Deliverable | Final payments | Final verifications | Final Project Report
Reporting period | Preferably up to six (6) months from the end date of the project and obligatorily by the 31/12/2023 |  | Up to two (2) months from the date of the final verification(s)
Reporting of eligible costs | Payment of costs (including costs related to the elaboration and submission of the Final Project Report and to the project administrative closure activities and the final verification fee). All core activities expenses should be invoiced before the end date of the project. Closure activities expenses, including the final verification fee can in any way be invoiced after the end date of the project. | Verification of all expenditure. Strongly recommended by 31.12.2023 | Reporting of all expenditure incurred paid out and verified.
Reporting of activities |  |  | Giving a qualitative summary of the project as a whole and detailing all project activities, achievement of outputs and results, deliverables produced. The financial data of the Final Project Report should also include the final verification fee.

## Slide 15: Specifications regarding the eligibility of expenditures
All expenditures related to the project implementation must be invoiced before the end date of the project. Expenditures related to the closure procedures are possible to be invoiced after the end date of the project.
All expenditures must be paid out until 31/12/2023 the latest, to be eligible within the framework of the Programme.
The bank charges for the transfer of the final EU contribution reimbursement will not be eligible.
Non-conformity with the Call for Proposals thresholds at project closure may be accepted
In all of the above cases, the LB will have the obligation to incorporate the respective information into the Final Project Report, and Final AF (AF for project completion), while no modification of the Partnership Agreement and the Subsidy Contract is required.

## Slide 16
Expenditure incurred by a PB after the submission of the Final AF by the LB to the MA/JS, is ineligible;
Before the issuance of the Completion Decision, Greek Beneficiaries should have completed all necessary administrative steps in order to balance the payments of the Public Investment Programme with the certified amounts of their expenditure.
For FLC purposes minor changes between the budget categories might take place at the end of the projects. The beneficiary should have the agreement of the Managing Authority for that changes which should be made before the finalization of the Final Project Report of the project.
If, no later than the closure of the Programme, the project is identified as revenue-generating, the MA is entitled to ask for a refund to the Programme in proportion to the public contribution granted.
Should a cost benefit analysis is required, this will be made before the closure of the project and at the PB’s expense unless otherwise indicated in their respective budget

## Slide 17
Amounts to be returned in view of the Project’s closure
eventual generation of income (due to interest-bearing bank account) and
the amounts received by your Organisation to date and finally certified, in view of setting off the financial part of implementation.
financial correction and recovery of the unduly or illegally paid amount

## Slide 18: CONTROL After project closure
The EU and Programme regulations indicate the open-to-control period after the project is closed
Project closure and the open-to-control period, of three (3) years from 31 December following the submission of the accounts in which the expenditure of the operation is included (according to Art. 140 of the CPR Regulation), or longer if foreseen at national level, require preparation from the start of project implementation

## Slide 19
Giorgos Papadopoulos
Head of Joint Secretariat Interreg IPA CBC Programme “Greece-Albania 2014-2020” +30 2310469685
gpapadopoulos@mou.gr
Thank you for your attention